## Φύλλο1
Task Description | Date | Duration | Week | Total Week Hours | Notes/Comments
Project Planning Research: Exploring strategies for effective project management. | 2023-08-25 | 2:47 | 08/21/2023 – 08/27/2023 | 3:58
Project Ideation & Time Planning: Researching project concepts and creating a structured timeline. | 2023-08-25 | 0:39 | 08/21/2023 – 08/27/2023 | 3:58
Project Management Setup: Establishing a project board, integrating a time tracking app, and creating a timesheet system. | 2023-08-27 | 0:32 | 08/21/2023 – 08/27/2023 | 3:58
Tech Stack Exploration: Researching the ideal technology stack for a potential project. | 2023-08-28 | 5:10 | 08/28/2023 – 09/03/2023 | 30:17
UI Design Skill Building: Exploring UI design principles and mastering tools like Figma and Sketch. | 2023-08-29 | 0:30 | 08/28/2023 – 09/03/2023 | 30:17
Rewatching the Video of the Orientation before I take the quiz. | 2023-08-30 | 0:09 | 08/28/2023 – 09/03/2023 | 30:17
Pre-Quiz Review: Revisiting the Orientation Video for quiz preparation. | 2023-08-30 | 0:08 | 08/28/2023 – 09/03/2023 | 30:17
Project Planning on Trello: Creating a comprehensive project plan and to-do list on the project management board. | 2023-08-30 | 0:59 | 08/28/2023 – 09/03/2023 | 30:17
Project Selection & Technology Research: Finalizing the project idea, exploring relevant technologies and tools, and completing intake and proposal surveys. | 8/31/2023 - 9/01/2023 | 12:44 | 08/28/2023 – 09/03/2023 | 30:17
Repository Setup: Establishing both a local and remote repository for version control. | 2023-09-01 | 0:04 | 08/28/2023 – 09/03/2023 | 30:17
Repository Connection: Linking the local repository to the remote repository. | 2023-09-01 | 0:03 | 08/28/2023 – 09/03/2023 | 30:17
Feature Objective Documentation: Recording key details and objectives for project features on Trello. | 2023-09-01 | 0:10 | 08/28/2023 – 09/03/2023 | 30:17
Figma Proficiency & Wireframing: Building expertise in Figma for wireframing the visual design of my web app. | 2023-09-01 | 2:01 | 08/28/2023 – 09/03/2023 | 30:17
Design Workflow Utilization: Leveraging OneNote for wireframing, Figma for UI layout, and Draw.io for creating sitemap diagrams. | 2023-09-02 | 8:18 | 08/28/2023 – 09/03/2023 | 30:17
Node.js & NPM Refresher: Updating and reinforcing my knowledge of Node.js and NPM. | 2023-09-04 | 3:57 | 09/04/2023 – 09/10/2023 | 34:52
Strategic Application Design Planning: Crafting an efficient planning process for my application's design. | 2023-09-05 | 4:40 | 09/04/2023 – 09/10/2023 | 34:52
Strategic Planning Advancement: Methodically shaping the application's roadmap, including user stories and feature enhancements. | 2023-09-06 | 3:10 | 09/04/2023 – 09/10/2023 | 34:52
Project Planning: Investigating novel strategies to enhance planning and execution efficiency. | 2023-09-06 | 0:45 | 09/04/2023 – 09/10/2023 | 34:52
Ongoing Efficiency Exploration: Continuously seeking ways to optimize project planning and execution. | 2023-09-06 | 1:27 | 09/04/2023 – 09/10/2023 | 34:52
Workflow Visualization Enhancement: Incorporating flowcharts to streamline and visually represent project workflows in my planning process. | 2023-09-06 | 1:30 | 09/04/2023 – 09/10/2023 | 34:52
JavaScript Fundamentals Mastery: Revisiting and strengthening my grasp of essential JavaScript concepts. | 2023-09-07 | 1:34 | 09/04/2023 – 09/10/2023 | 34:52
Refreshing my memory on Async/Await and Promises, Object Oriented Programming, DOM and Events. | 2023-09-08 | 3:05 | 09/04/2023 – 09/10/2023 | 34:52
Database Design Learning Journey: Acquiring skills for database planning and design. | 2023-09-09 | 6:45 | 09/04/2023 – 09/10/2023 | 34:52
App Core Operations Definition: Clarifying the fundamental functionalities of my application. | 2023-09-10 | 4:46 | 09/04/2023 – 09/10/2023 | 34:52
Technology Assessment: Assessing and selecting the most suitable technologies for app development. | 2023-09-10 | 3:14 | 09/04/2023 – 09/10/2023 | 34:52
Design Documents Done: Ready to move forward. | 2023-09-11 | 9:25 | 09/11/2023 – 09/17/2023 | 39:40
UI Mastery Journey: Diving into React for web development. | 2023-09-12 | 6:54 | 09/11/2023 – 09/17/2023 | 39:40
React Practice Session: Strengthening skills and knowledge. | 2023-09-13 | 3:35 | 09/11/2023 – 09/17/2023 | 39:40
Folder Structure Analysis: Navigating the organization of web projects. | 2023-09-13 | 0:29 | 09/11/2023 – 09/17/2023 | 39:40
Web App Folder Setup: Crafting the organizational backbone. | 2023-09-13 | 2:42 | 09/11/2023 – 09/17/2023 | 39:40
NPM Package Hunt: Seeking tools to streamline development. | 2023-09-13 | 3:02 | 09/11/2023 – 09/17/2023 | 39:40
NPM Package Deep Dive: Delving into the functionalities. | 2023-09-15 | 4:26 | 09/11/2023 – 09/17/2023 | 39:40
UI Development Kickoff: Applying React skills to the project. | 2023-09-16 | 2:08 | 09/11/2023 – 09/17/2023 | 39:40
Modeling Data with Mongoose: Organizing the backend. | 2023-09-17 | 0:44 | 09/11/2023 – 09/17/2023 | 39:40
Security Learning Journey: Exploring Authentication and Authorization. | 2023-09-17 | 6:15 | 09/11/2023 – 09/17/2023 | 39:40