## Φύλλο1
Task Description | Date | Duration | Week | Total Week Hours | Notes/Comments
Project Planning Research: Exploring strategies for effective project management. | 2023-08-25 | 2:47 | 08/21/2023 – 08/27/2023 | 3:58
Project Ideation & Time Planning: Researching project concepts and creating a structured timeline. | 2023-08-25 | 0:39 | 08/21/2023 – 08/27/2023 | 3:58
Project Management Setup: Establishing a project board, integrating a time tracking app, and creating a timesheet system. | 2023-08-27 | 0:32 | 08/21/2023 – 08/27/2023 | 3:58
Tech Stack Exploration: Researching the ideal technology stack for a potential project. | 2023-08-28 | 5:10 | 08/28/2023 – 09/03/2023 | 30:17
UI Design Skill Building: Exploring UI design principles and mastering tools like Figma and Sketch. | 2023-08-29 | 0:30 | 08/28/2023 – 09/03/2023 | 30:17
Rewatching the Video of the Orientation before I take the quiz. | 2023-08-30 | 0:09 | 08/28/2023 – 09/03/2023 | 30:17
Pre-Quiz Review: Revisiting the Orientation Video for quiz preparation. | 2023-08-30 | 0:08 | 08/28/2023 – 09/03/2023 | 30:17
Project Planning on Trello: Creating a comprehensive project plan and to-do list on the project management board. | 2023-08-30 | 0:59 | 08/28/2023 – 09/03/2023 | 30:17
Project Selection & Technology Research: Finalizing the project idea, exploring relevant technologies and tools, and completing intake and proposal surveys. | 8/31/2023 - 9/01/2023 | 12:44 | 08/28/2023 – 09/03/2023 | 30:17
Repository Setup: Establishing both a local and remote repository for version control. | 2023-09-01 | 0:04 | 08/28/2023 – 09/03/2023 | 30:17
Repository Connection: Linking the local repository to the remote repository. | 2023-09-01 | 0:03 | 08/28/2023 – 09/03/2023 | 30:17
Feature Objective Documentation: Recording key details and objectives for project features on Trello. | 2023-09-01 | 0:10 | 08/28/2023 – 09/03/2023 | 30:17
Figma Proficiency & Wireframing: Building expertise in Figma for wireframing the visual design of my web app. | 2023-09-01 | 2:01 | 08/28/2023 – 09/03/2023 | 30:17
Design Workflow Utilization: Leveraging OneNote for wireframing, Figma for UI layout, and Draw.io for creating sitemap diagrams. | 2023-09-02 | 8:18 | 08/28/2023 – 09/03/2023 | 30:17
Node.js & NPM Refresher: Updating and reinforcing my knowledge of Node.js and NPM. | 2023-09-04 | 3:57 | 09/04/2023 – 09/10/2023 | 34:52
Strategic Application Design Planning: Crafting an efficient planning process for my application's design. | 2023-09-05 | 4:40 | 09/04/2023 – 09/10/2023 | 34:52
Strategic Planning Advancement: Methodically shaping the application's roadmap, including user stories and feature enhancements. | 2023-09-06 | 3:10 | 09/04/2023 – 09/10/2023 | 34:52
Project Planning: Investigating novel strategies to enhance planning and execution efficiency. | 2023-09-06 | 0:45 | 09/04/2023 – 09/10/2023 | 34:52
Ongoing Efficiency Exploration: Continuously seeking ways to optimize project planning and execution. | 2023-09-06 | 1:27 | 09/04/2023 – 09/10/2023 | 34:52
Workflow Visualization Enhancement: Incorporating flowcharts to streamline and visually represent project workflows in my planning process. | 2023-09-06 | 1:30 | 09/04/2023 – 09/10/2023 | 34:52
JavaScript Fundamentals Mastery: Revisiting and strengthening my grasp of essential JavaScript concepts. | 2023-09-07 | 1:34 | 09/04/2023 – 09/10/2023 | 34:52
Refreshing my memory on Async/Await and Promises, Object Oriented Programming, DOM and Events. | 2023-09-08 | 3:05 | 09/04/2023 – 09/10/2023 | 34:52
Database Design Learning Journey: Acquiring skills for database planning and design. | 2023-09-09 | 6:45 | 09/04/2023 – 09/10/2023 | 34:52
App Core Operations Definition: Clarifying the fundamental functionalities of my application. | 2023-09-10 | 4:46 | 09/04/2023 – 09/10/2023 | 34:52
Technology Assessment: Assessing and selecting the most suitable technologies for app development. | 2023-09-10 | 3:14 | 09/04/2023 – 09/10/2023 | 34:52
Design Documents Done: Ready to move forward. | 2023-09-11 | 9:25 | 09/11/2023 – 09/17/2023 | 39:40
UI Mastery Journey: Diving into React for web development. | 2023-09-12 | 6:54 | 09/11/2023 – 09/17/2023 | 39:40
React Practice Session: Strengthening skills and knowledge. | 2023-09-13 | 3:35 | 09/11/2023 – 09/17/2023 | 39:40
Folder Structure Analysis: Navigating the organization of web projects. | 2023-09-13 | 0:29 | 09/11/2023 – 09/17/2023 | 39:40
Web App Folder Setup: Crafting the organizational backbone. | 2023-09-13 | 2:42 | 09/11/2023 – 09/17/2023 | 39:40
NPM Package Hunt: Seeking tools to streamline development. | 2023-09-13 | 3:02 | 09/11/2023 – 09/17/2023 | 39:40
NPM Package Deep Dive: Delving into the functionalities. | 2023-09-15 | 4:26 | 09/11/2023 – 09/17/2023 | 39:40
UI Development Kickoff: Applying React skills to the project. | 2023-09-16 | 2:08 | 09/11/2023 – 09/17/2023 | 39:40
Modeling Data with Mongoose: Organizing the backend. | 2023-09-17 | 0:44 | 09/11/2023 – 09/17/2023 | 39:40
Security Learning Journey: Exploring Authentication and Authorization. | 2023-09-17 | 6:15 | 09/11/2023 – 09/17/2023 | 39:40
Database Schema Expansion: Introduced two new schemas, 'photos' and 'languages,' to enhance database functionality. | 2023-09-18 | 1:55 | 09/18/2023 – 09/24/2023 | 36:50
Database Update: Integrated 'languages' into the database for expanded functionality. | 2023-09-19 | 0:43 | 09/18/2023 – 09/24/2023 | 36:50
Form Development Milestone: Successfully constructed login, registration, and profile creation forms. | 2023-09-19 | 3:20 | 09/18/2023 – 09/24/2023 | 36:50
Component Integration Research: Exploring npm documentation for seamless integration of desired components into my application. | 2023-09-19 | 1:19 | 09/18/2023 – 09/24/2023 | 36:50
Express App Route Documentation: Defining and documenting the application's routes for clarity and reference. | 2023-09-19 | 0:12 | 09/18/2023 – 09/24/2023 | 36:50
User Registration and Authentication Design Document: Crafting a comprehensive blueprint for routes and controllers. | 2023-09-20 | 2:22 | 09/18/2023 – 09/24/2023 | 36:50
Express Error Handling Research: Deepening my understanding of error handling strategies within the Express framework. | 2023-09-20 | 3:25 | 09/18/2023 – 09/24/2023 | 36:50
Error Handling Implementation: Strengthened my Express app with robust error handling. | 2023-09-21 | 2:15 | 09/18/2023 – 09/24/2023 | 36:50
Password and JWT Authentication Mastery: Exploring techniques and methods for secure password management and authentication using JWT. | 2023-09-21 | 3:49 | 09/18/2023 – 09/24/2023 | 36:50
Security and Authentication Implementation: Incorporating login and registration functionalities with protection and JWT-based authentication logic while utilizing Postman for thorough testing. | 2023-09-21 | 4:34 | 09/18/2023 – 09/24/2023 | 36:50
Protected Login and Registration Features: Successfully integrated login and registration functionalities with robust security measures. | 2023-09-22 | 3:19 | 09/18/2023 – 09/24/2023 | 36:50
Forgot Password Research: Exploring methods to implement the 'forgot password' feature and integrate email functionality using Nodemailer. | 2023-09-22 | 1:31 | 09/18/2023 – 09/24/2023 | 36:50
Enhanced User Model: Incorporated key functions, including 'createPasswordResetToken' and 'changedPasswordAfter,' along with middleware to update 'passwordChangedAt' timestamp for password changes. | 2023-09-22 | 2:52 | 09/18/2023 – 09/24/2023 | 36:50
Model Refactoring for Efficiency: Streamlined and reorganized models to align with the application's functionalities. | 2023-09-23 | 2:11 | 09/18/2023 – 09/24/2023 | 36:50
User Routes Planning: Brainstorming and strategizing to determine the most crucial user routes to implement. | 2023-09-24 | 0:45 | 09/18/2023 – 09/24/2023 | 36:50
Authorization Research: Exploring in-depth to enhance understanding of the principles and practices of authorization. | 2023-09-24 | 1:00 | 09/18/2023 – 09/24/2023 | 36:50
Role-Based Access Control Documentation: Roles and permissions documentation, accompanied by middleware implementation to enforce access restrictions based on user roles. | 2023-09-24 | 0:56 | 09/18/2023 – 09/24/2023 | 36:50
Password Reset Functionality Added: Successfully implemented basic password reset functionality, utilizing Mailtrap for email testing. Enhanced the 'forgotPassword' controller with Nodemailer for email sending, set up a testing 'sendEmail' function, and integrated it into the 'forgotPassword' controller. | 2023-09-25 | 1:53 | 09/25/2023 – 10/01/2023 | 20:28
Reset Password Functionality Implemented: Created the 'resetPassword' controller function and tested it using Postman and Mailtrap for a secure and efficient reset process. | 2023-09-25 | 0:41 | 09/25/2023 – 10/01/2023 | 20:28
Password Update Functionality Added: Implemented the 'updatePassword' controller function, for exclusive access by logged-in users and tested it using Postman to ensure robust security and functionality. | 2023-09-25 | 0:40 | 09/25/2023 – 10/01/2023 | 20:28
Security-Related Error Debugging: Focused troubleshooting and resolution of password and security-related issues. | 2023-09-25 | 0:35 | 09/25/2023 – 10/01/2023 | 20:28
User Routes Refactor: Optimized endpoint naming, introduced user data management functions, filtered inactive users with middleware, enhanced filterObj for nested fields, and adapted updateUser for admin changes. | 2023-09-25 | 1:31 | 09/25/2023 – 10/01/2023 | 20:28
Security Enhancement: Studying effective security practices and implementing the express-rate-limit module for added protection and prevention of request overloading. | 2023-09-25 | 0:21 | 09/25/2023 – 10/01/2023 | 20:28
Security Header Setup: Set Security HTTP Headers with helmet to help defend against various types of attacks, leaks, and vulnerabilities. | 2023-09-25 | 0:06 | 09/25/2023 – 10/01/2023 | 20:28
Enhanced Security Middleware: Installed express-mongo-sanitize and xss-clean to safeguard against MongoDB query injection and XSS attacks through middleware. | 2023-09-26 | 0:12 | 09/25/2023 – 10/01/2023 | 20:28
Middleware Integration and Code Cleanup: Integrated request logging with Morgan middleware, eliminated duplicate responses in the register controller, removed redundant validation error functions in the errorController, and implemented logout functionality. | 2023-09-26 | 0:09 | 09/25/2023 – 10/01/2023 | 20:28
Authentication Debugging: Addressed issues during Postman testing involving cookies and Bearer tokens, requiring debugging to resolve unexpected behaviors. | 2023-09-26 | 2:02 | 09/25/2023 – 10/01/2023 | 20:28
Profile Completion Enhancement: Implementing a mandatory profile completion step post-registration to ensure users provide essential details before accessing core platform functionalities. | 2023-09-26 | 2:05 | 09/25/2023 – 10/01/2023 | 20:28
Redux Learning Journey: Embarking on the path to gain expertise in Redux. | 2023-09-27 | 3:12 | 09/25/2023 – 10/01/2023 | 20:28
Redux Setup and Integration: Established Redux for state management, integrated react-toastify for alert displays, and implemented alert and auth slices for login, registration, and user authentication. | 2023-09-27 | 1:39 | 09/25/2023 – 10/01/2023 | 20:28
Route Protection and Authentication Enhancement: Introduced PrivateRoute component to protect authenticated routes, improved login and registration with enhanced authentication logic, and refactored authController.js for more efficient cookie handling and DRY (Don't Repeat Yourself) code. | 2023-09-27 | 0:32 | 09/25/2023 – 10/01/2023 | 20:28
Incorporated Registration Flow Design: Integrated the design of the registration flow into the 'User Registration and Authentication Routes & Controllers' documentation. | 2023-09-27 | 0:16 | 09/25/2023 – 10/01/2023 | 20:28
New Components & Folder Restructuring: Added ProfileImageUpload and LocationsAutocomplete components, integrate Google Places API, and restructure component folders. | 2023-09-28 | 2:34 | 09/25/2023 – 10/01/2023 | 20:28
Component Communication Enhancement: Revised the ProfileCreationForm and ProfileImageUpload components to establish a communication channel. Now, when an image is selected in the ProfileImageUpload component, it's transmitted back to the ProfileCreationForm component, updating its state and preparing the image for submission. | 2023-09-29 | 0:49 | 09/25/2023 – 10/01/2023 | 20:28
LocationsAutocomplete Callback Update: Modified the onPlaceSelected callback to receive an object with latitude, longitude, and formatted address when invoked upon location selection. | 2023-09-29 | 0:52 | 09/25/2023 – 10/01/2023 | 20:28
Dropdown Language Filtering: Implemented filtering in language dropdowns to exclude selected language from options in other language dropdown menus. | 2023-09-30 | 0:16 | 09/25/2023 – 10/01/2023 | 20:28
Cloudinary Integration for Image Upload: Incorporated the cloudinary and multer-storage-cloudinary packages and configured Cloudinary with multer to facilitate seamless image uploads. | 2023-10-01 | 0:24 | 10/02/2023 – 10/08/2023 | 18:58
Controller Function Update: Enhanced the createProfile controller function to handle multipart form data, extract specific fields, and perform user updates in the database. | 2023-10-01 | 2:00 | 10/02/2023 – 10/08/2023 | 18:58
Controller Function Update: In the createProfile controller function, I've implemented special handling for languages. This involves retrieving related language documents from the database and substituting language names with their corresponding database IDs during processing. | 2023-10-02 | 1:23 | 10/02/2023 – 10/08/2023 | 18:58
Client Authentication with Redux: Successfully finalized the authentication slice on the client-side using Redux. Additionally, I've updated the routing in App.jsx by integrating my routing component for a more comprehensive application structure. | 2023-10-02 | 0:39 | 10/02/2023 – 10/08/2023 | 18:58
Redux Toolkit Advancements: Expanded my knowledge and expertise in Redux Toolkit for enhanced state management and application development. | 2023-10-02 | 0:30 | 10/02/2023 – 10/08/2023 | 18:58
Updated 'photos' Field: Enhanced the 'photos' field in the user model to include functionality similar to the 'profilePicture' field, storing both URL and filename. | 2023-10-02 | 0:04 | 10/02/2023 – 10/08/2023 | 18:58
Added Age Calculation: Implemented a function in the user schema to calculate the user's age. | 2023-10-02 | 0:04 | 10/02/2023 – 10/08/2023 | 18:58
Controller Function Update: Modified the createProfile controller function to accommodate scenarios where the user doesn't provide a profile picture. | 2023-10-02 | 0:04 | 10/02/2023 – 10/08/2023 | 18:58
AuthSlice and LoginForm Logic Refinement: Implemented fixes and improvements to enhance the functionality and reliability of the authSlice in Redux and the LoginForm component. | 2023-10-05 | 0:56 | 10/02/2023 – 10/08/2023 | 18:58
Navbar Authentication Update: Implemented functionality to dynamically update the Navbar based on the authentication state of the user. | 2023-10-05 | 1:10 | 10/02/2023 – 10/08/2023 | 18:58
User-Friendly Alerts: Designed custom alert messages for enhanced user experience. | 2023-10-06 | 0:06 | 10/02/2023 – 10/08/2023 | 18:58
User Avatar Dropdown: Developed a dropdown menu for the user avatar in the navbar, featuring 'My Profile,' 'Settings,' and 'Log Out' links. | 2023-10-06 | 0:40 | 10/02/2023 – 10/08/2023 | 18:58
Personal Profile Page: Designed and developed a PersonalProfile page, functioning as a profile preview exclusively for logged-in users. | 2023-10-07 | 2:21 | 10/02/2023 – 10/08/2023 | 18:58
Profile Editing Enhancement: Enhanced the LocationsAutocomplete component to display previously saved locations during profile editing. | 2023-10-08 | 0:10 | 10/02/2023 – 10/08/2023 | 18:58
Profile Editing Enhancement: Improved the ProfileImageUpload component to show the user's profile picture when editing the profile. | 2023-10-08 | 0:13 | 10/02/2023 – 10/08/2023 | 18:58
Profile Editing Enhancement: Updated the updateMe controller function on the server to correctly process and update data received from the client. | 2023-10-08 | 2:12 | 10/02/2023 – 10/08/2023 | 18:58
Profile Editing Enhancement: Expanded the authSlice.js by introducing a reducer to update the user's avatar in the navbar when the user changes their profile image. | 2023-10-08 | 0:04 | 10/02/2023 – 10/08/2023 | 18:58
Profile Editing Suite: Integrated the ProfileEditForm component, allowing users to edit their profiles and change their email and username (password changes not supported), into the EditProfile page, which provides an efficient platform for users to view and edit their associated data. | 2023-10-08 | 5:53 | 10/02/2023 – 10/08/2023 | 18:58
Redux State Enhancement: Streamlined the Redux state management by removing the reducer for updating the user avatar in the navbar and replaced it with a single, comprehensive Redux Action to update all user data. | 2023-10-08 | 0:03 | 10/02/2023 – 10/08/2023 | 18:58
Image Handling Controller Functions: Developed controller functions to manage the uploading and deletion of user images, including the corresponding routes to enable these operations. | 2023-10-09 | 2:45 | 10/9/2023 – 10/15/2023 | 17:18
Photo Upload Component: Integrated the Ant Design 'PicturesWall' component to facilitate photo uploads in the application. | 2023-10-09 | 1:34 | 10/9/2023 – 10/15/2023 | 17:18
Photo Display and Deletion Logic: Implemented logic to showcase the user's photos in the PicturesWall component, enabling easy deletion from both the database and Cloudinary. | 2023-10-09 | 4:45 | 10/9/2023 – 10/15/2023 | 17:18
Carousel Modal Integration: Successfully incorporated Ant Design's Modal and Carousel components to create a modal carousel mode for improved user experience. | 2023-10-09 | 0:20 | 10/9/2023 – 10/15/2023 | 17:18
Photo Upload Issue Resolution: Encountered a challenge with photo uploading to the database and Cloudinary in the upload component and backend code. Successfully resolved the issue, ensuring synchronized photo uploads to both the database and Cloudinary for seamless functionality. | 2023-10-09 | 4:33 | 10/9/2023 – 10/15/2023 | 17:18
Cloudinary Configuration Enhancement: Introduced image resizing functionality in the Cloudinary configuration for improved image handling. | 2023-10-09 | 0:02 | 10/9/2023 – 10/15/2023 | 17:18
Route and Controller Enhancements: Implemented a new route for accessing a single user by their ID and improved the getAllUsers() controller function by filtering out the current user before sending the response. | 2023-10-14 | 0:22 | 10/9/2023 – 10/15/2023 | 17:18
User Profile Enhancements: Introduced a virtual property in the user schema to maintain age as a single source of truth. | 2023-10-14 | 0:08 | 10/9/2023 – 10/15/2023 | 17:18
User Profile Enhancements: Designed a User Card component for displaying essential user details, clickable to redirect to the user's full profile. | 2023-10-14 | 1:35 | 10/9/2023 – 10/15/2023 | 17:18
User Profile Enhancements: Created the Public Profile page for user profiles to be publicly viewable. | 2023-10-14 | 1:12 | 10/9/2023 – 10/15/2023 | 17:18
Chat Page Design: Created the design for the chat page, ensuring a user-friendly and visually appealing interface for seamless communication. | 2023-10-16 | 4:34 | 10/16/2023 – 10/22/2023
Profile Page Enhancement: Implemented an animated chat initiation button on the Profile Page of every user, enhancing the user experience for starting conversations. | 2023-10-16 | 0:06 | 10/16/2023 – 10/22/2023